## Blue
Entrepreneurship Club
Pixel Pioneers
Project start date: | 2024-11-03 | [10 empty] | Scrolling increment: | [5 empty] | 9
Milestone marker: | 1 | 1 |  |  | November | [20 empty] | December
 | time axis 2024-11-12 to 2025-01-06
Milestone description | Assigned to | Progress | Start | Days | time axis 2024-11-12 to 2025-01-06
Milestone 6
Finalize CSS
Finalize Contact CSS | Ella | 100% | 2024-11-03 | 10
Finalize Home CSS | Lucas | 100% | 2024-11-03 | 10
Finalize Admin CSS | Lucas/Ella | 100% | 2024-11-03 | 10
Finalize Footer/Header Design
Design/ implement Footer | Lucas | 100% | 2024-11-03 | 10
Media Adjustments for Header | Ella | 100% | 2024-11-03 | 10
Fix Sidebar Animation and Page Shrink | Ella | 100% | 2024-11-03 | 10
Finalize Footer/Header Design
Design event display logic | Lennox | 100% | 2024-11-03 | 10
Elevate the HTML structure & CSS styling of contact page | Lennox | 100% | 2024-11-03 | 15
Elevate the HTML structure & CSS styling of schedule page | Lennox | 100% | 2024-11-03 | 15
Milestone 7
Admin Basic Functionality
Admin Login Security | Lucas | 100% | 2024-11-11 | 7
Admin Display Members on Page | Lucas/Ella | 100% | 2024-11-11 | 7
Admin Display Events on Page | Lucas/Lennox | 100% | 2024-11-11 | 7
Admin Backend Functionality
Add / Delete Members functional | Ella / Lucas | 100% | 2024-11-11 | 7
Design & Code Admin side events page look, feel & data intake | Lennox / Lucas | 100% | 2024-11-11 | 7
Edit Member Functionality | Lucas | 100% | 2024-11-11 | 7
Contact Form Security
Implement back-end input sanitization | Lennox | 100% | 2024-11-11 | 7
Code js&PHP&Other dependencies to harvest user input in contact form | Lennox | 100% | 2024-11-11 | 7
Intergrate PHPMailer for more secure mail system | Lennox | 100% | 2024-11-11 | 7 | bar: 2024-12-31
Milestone 8
Client Approval and Suggestions
Meet with client and show draft of website | All | 100% | 2024-12-31 | 1 | bar: 2024-12-31
Finalize Hosting and Domain with client | All | 100% | 2024-12-31 | 1
Finalize photos/ bios | Ella/Lennox | 100% | 2024-12-31 | 1 | bar: 2024-12-16
Finish Client Suggestions
Tasks TBD by client | All | 100% | 2024-11-28 | 14
Finalize any unfinished backend | Lucas | 100% | 2024-11-28 | 14
Finalize media width designs | Ella | 100% | 2024-11-28 | 14
Present Project
Upload all documents and website | All | 100% | 2024-12-16 | 1
Send final message with instructions to client after completion | All | 100% | 2024-12-16 | 1
Present Project to Class | All | 100% | 2024-12-16 | 1
To add more data, Insert new rows ABOVE this one